## Slide 1
EAP Kickoff
Enterprise Application Project
Motopp 12-week Software Development Project

## Slide 2
Welcome to the EAP
This is a professional software development project
Not a classroom exercise, but real responsibility
You work in a Scrum team and deliver a real product
You are responsible for planning, quality, and delivery
Staff coaches and observes but does not take over your roles
Professional software development mindset

## Slide 3
The Product: Enterprise Application Portal
What are you building?
A centralized, web-based platform for handling internal requests such as hardware, software access, and approvals
Technical Scope
Web-based frontend and backend
Authentication and authorization
Request and approval workflows
CI/CD pipelines and automated testing
Logging, monitoring, and documentation
Project Details
DURATION
12 weeks
SPRINTS
2-week cycles
FRAMEWORK
Scrum + DevOps
Realistic enterprise internal application

## Slide 4
Product Vision: What Does the EAP Do?
Core Workflow
STEP 1
Employee submits request
→
STEP 2
Manager/Admin approves
→
STEP 3
Request fulfilled
Example Use Cases
New laptop request
Software license access
Production environment access
Office equipment
User Roles
Requester: Submits requests
Approver: Reviews and approves
Admin: Manages system
Key Features
Request submission forms
Approval workflows
Status tracking
Email notifications
Request history
Admin dashboard
Product Owner will refine detailed requirements during Sprint 1
High-level vision - details in Product Backlog

## Slide 5
Team Roles - These Belong to You
Product Owner (intern role)
Decides on scope and priorities. Staff do NOT make product decisions.
Scrum Master (intern role)
Facilitates Scrum events. Staff are Scrum Coaches, NOT Scrum Masters.
DevOps (team responsibility)
Pipelines, deployments, operational issues. Staff do NOT solve this.
Development (shared responsibility)
All team members build, test, and improve the product.
These roles belong to you

## Slide 6
Working with Scrum
Sprint Structure
2-week sprints
Sprint Planning, Daily Scrum, Sprint Review, Retrospective
Scrum Master facilitates, everyone participates
Definition of Ready
When is a backlog item ready to enter a Sprint?
Goal is clear
Acceptance criteria defined
Small enough for 1 sprint
Definition of Done
When is work truly finished?
Code reviewed
Tests run in pipeline
Deployed and documented
Templates available as starting point

## Slide 7
Quality & Professionalism
Mistakes are allowed.
Ignoring problems is not.
Expectations
Code is reviewed
Tests run in the pipeline
Transparency about delivery issues
Respect quality and processes
Professional = how you respond
Investigate calmly when problems occur
Communicate clearly
Make decisions as a team
Be transparent about issues
Focus on professional behavior, not avoiding mistakes

## Slide 8
How Staff Works
Our roles
Scrum Coaches
Support and challenge your process
Sponsors
Strategic direction and escalation point
Observers
Watch behavior and decision-making
✓ What we DO
Ask questions
Challenge reasoning
Observe and give feedback
Coach on process
✗ What we DON'T do
Take over Scrum roles
Make product decisions
Solve technical problems
Run the project for you
"If we step in too much, we are doing something wrong."
Coaching, not rescuing

## Slide 9
Practical Arrangements
Working Hours & Location
OFFICE DAY
1 day per week
REMOTE
Other days
TOOL
MS Teams
Available Tooling & Infrastructure
Source Control
GitHub (private repos)
Project Management
Jira (paid license)
CI/CD
GitHub Actions
Deployment
TransIP VPS (Linux)
Access Details
Credentials via email before Sprint 1
Communication
Open, early, visible
Expectations
Stay calm, be transparent, decide together

## Slide 10
Sprint 1: Setup Tasks
These setup tasks are part of Sprint 1
1. Confirm Roles
Who is Product Owner, Scrum Master, and DevOps lead?
2. Setup Tooling Access
Configure GitHub, Jira, and VPS access with provided credentials
3. Discuss DoR/DoD
Read templates as a team and agree to use them
4. First Backlog Items
Product Owner prepares initial items
5. Team Agreements
Daily Scrum time? Office day? Communication agreements
6. Architecture Setup
Governance and decision-making details during Sprint 1
Essential setup for project success

## Slide 11
Available Project Documents
Strategy & Governance
Project Initiation Document (PID)
Defines project objectives, scope, and governance
Intern-Facing Documents
Sprint Guide for Interns
How sprints work and what's expected
Intern Onboarding Guide
Team roles, expectations, and workflows
Definition of Ready Template
When backlog items are ready for Sprint
Definition of Done Template
When work is truly finished
Access & Location
All documents are available in:
Cohort Baseline Archive
What to read first:
1. Intern Onboarding Guide
2. Sprint Guide
3. DoR/DoD Templates
These are your reference documents throughout the project
Cohort Baseline Archive - your project reference

## Slide 12
Team Roles - These Belong to You
Product Owner (intern role)
Decides on scope and priorities. Staff do NOT make product decisions.
Scrum Master (intern role)
Facilitates Scrum events. Staff are Scrum Coaches, NOT Scrum Masters.
DevOps (team responsibility)
Pipelines, deployments, operational issues. Staff do NOT solve this.
Development (shared responsibility)
All team members build, test, and improve the product.
These roles belong to you